## Start Here
RISK REGISTER
Free Template — PM AI Prompt Toolkit
PMBOK® 8 Performance Domain: RISK ¦ Focus Area: Planning / Monitoring & Controlling
HOW TO USE THIS TEMPLATE
1. Go to the ‘Risk Register’ tab. Row 5 has an example already filled in — use it as a guide, then delete it before sharing with your client.
2. Fill in Risk Description, Category, Likelihood and Impact for each risk. Likelihood and Impact use dropdown lists (click the cell to see options).
3. Risk Score and Risk Level are calculated automatically — don't type into those columns.
4. Check the ‘Risk Matrix’ tab any time for a visual heatmap of where your risks sit.
GENERATE RISKS FASTER WITH AI
Paste this into ChatGPT / Claude / Copilot to get a first draft of 10+ risks for your project in seconds:
Act as a PM building a Risk Register for this project.
Project: [PROJECT NAME]
Project type/industry: [e.g. hospital BMS install, factory automation]
Known concerns so far: [LIST ANY KNOWN RISKS]
Contract type: [e.g. fixed price, RM X, X months]
Site conditions: [e.g. live hospital, restricted access hours]
List at least 10 risks typical for this type of project with:
Risk Description, Category, Likelihood (1-5), Impact (1-5),
Response Strategy (Avoid/Mitigate/Transfer/Accept), Mitigation
Action, and Owner — formatted so I can paste straight into a table.
RISK LEVEL LEGEND
1–4 Low
5–9 Medium
10–14 High
15–25 Critical
WANT MORE?
This Risk Register is 1 of 17 AI-ready PM templates in the full PM AI Prompt Toolkit — covering everything from Project Charter to Closure Report, PMBOK® 8-aligned. [YOUR STORE LINK HERE]

## Risk Register
Risk ID | Date Identified | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Response Strategy | Mitigation Action | Owner | Status | Last Updated
R001 | 01-Jan-2026 | Delay in RFID reader delivery from overseas vendor due to customs clearance | Resource | 3 | 4 | 12 | High | Mitigate | Place order 6 weeks ahead of install date; identify local backup supplier | Procurement Lead | Open | 01-Jan-2026
Note on A2: Example row — delete before sharing with your client.

## Risk Matrix
RISK HEATMAP (Likelihood × Impact)
Reference grid — same scoring used in the Risk Register tab (Score = Likelihood × Impact).
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
LEGEND
1–4 Low
5–9 Medium
10–14 High
15–25 Critical